## Sheet1
Tester | Sr.No | Issues Description | Dev- Comments | Retest 1: Status | Mani
Reshma | 1 | Expand view: Open a page from menu/submenu Click any other menu/submenu. Clicked menu is not expanding | Fixed | PASS
Reshma | 2 | Expand view: Menu not retaining the selection and collapses for few pages and Breadcrums also not showing. (eg: Technical>PMS>Job status Technical>PMS>Job history ) | Fixed | PASS
Reshma | 3 | Expand view: Menu disappears for few pages. (eg: Purchase>ASL>Manage Contacts Technical>Worklist>Worklist Calendar ) | These pages are not inherited from master page. | Needs to discuss
Reshma | 4 | Breadcrums incorrect for few pages (eg: Dashboard Operations>Vessel movement>port Calls) | Fixed | PASS
Reshma | 5 | Breadcrums not showing for few pages (eg: Technical>Job status Technical>Jobhistory) | Fixed | PASS
Reshma | 6 | Menu at bottom hides behind when scroll though spaces are available | Scrollbar height id increase from 800px to 850px | Fail : Now scrollbar disappears on scrolling to bottom | Need screenshot
Reshma | 7 | Collapse view: Selected menu icon and menus are not highlighted/retained | Out of development scope. | Needs to discuss
Reshma | 8 | Menu/Submenus are not expand and collapse smoothly instead it's flickering | As the Menu is developed using Javascript and css that’s why it will not behave as smoothly as the ones developed using bootstrap and jquery. | PASS
Reshma | 9 | Collapse view: Menus changed to Expand view once few pages are clicked. For some pages menu expand and closing. (eg: Technical>PMS>Job status Technical>PMS>Job history ) | Fixed | PASS
Nilam | 10 | Expand View: Menu hangs for below steps Open Admin>Dashboard Collapse Admin Menu Now menu hangs and not able to expand any menu/pages | Fixed | PASS
Reshma | 11 | Breadcrum text color is different in few pages. 1. Technical>PMS>Unplanned Job details 2. Purchase>Contract Pricing>Create new contract 3.Purchase>Contract Pricing> Non Contract items 4. Purchase>Contract Pricing>Copy Contract | Fixed | PASS
Reshma | 12 | Menu and Breadcrumbs disappeared for below pages. Purchase>ASL>Manage Contacts | No master page applied, as in original project also this page don’t have master page | Noted
Reshma | 13 | Collapse view: No linespace if log menu names wrapped to next line. | line space is adjusted as possible as we can , We have limitation here for this because of multipal menu | PASS
Reshma | 14 | Baloon> Report Issue link not working | Fixed | PASS
Reshma | 15 | User settings options in header should be removed | Removed | PASS
Nilam | 16 | Menu load/expand/collapse performance is very slow in Mac-Safari |  | Pending for Mac, Pass in Desktop
Nilam | 17 | Collapse View: Submenus are not scrollable and can not view full submenu list |  | Fail -Issue still exist
Nilam | 18 | Collapse View: Snippets are overlapping ->in default screen for the submenus(Mac Safari) -> if screen size is decreased for other browsers | resolve for other browser has to check for Mac | Pending for Mac, Pass in Desktop
kiran | 19 | Breadcrum arrow not displaying | Resolved = Because of blocking some sites, arrow icon which are call from font awasome are not displaying . So as per our policy this icons are replaced with icon8 font icon | PASS
kiran | 20 | Help icon not desplaying | Same issue as above = Resolved | PASS
Nidhi | 21 | Icons size and space between them are not consistent in Menu Design(Confirmed w/ Bikash) |  | NEW
Nidhi | 22 | Collapse view: Pagination is overlapping on menu.Screenshot is shown on sheet 2 |  | NEW
Nidhi | 23 | Collapse view: Unable to open all submenus, only 1st sub menu expanding though user tries to expand other sub menus |  | NEW
Nidhi | 24 | Collapse view: Tooltip and dropdown is overlapping on menu.Screenshot is shown on sheet 2 |  | NEW
Arati | 25 | Breadcrums not showing. Admin>Office Settings>Dashboard Snippets |  | NEW
Arati | 26 | Line space required between text field and menu tables for all pages |  | NEW | Remove this
Arati | 27 | Scrollbar – User should be able to drag and scroll the menu scrollbar (from JIT#13602) |  | NEW
Arati | 28 | Extra Textlink "Add Fontawesome font" and input field appears Admin>Menu Management>Create Menu |  | NEW
Arati | 29 | lineSpace is required between contents list for all pages. |  | NEW | Remove this
Arati | 30 | Jibe logo on login page and jibe logo on above menu should be of same size |  | NEW
Arati | 31 | Line space required between text field in popup. |  | NEW | Remove this
Arati | 32 | Class content and Assembly content overlapped. Admin > OnBoard Settings > Project Mgmt |  | NEW
Arati | 33 | Image path, Delete icon and E-Tickets are overlapping . E-Teckets is partially visible. Admin> OnBoard Settings >Navigation Project Mgmt |  | NEW
Arati | 34 | Attach path content is not present in Edit popup and save button. Admin > Office Settings > Office Attachment Rule Admin > Office Settings > Vessel Attachment Rule |  | NEW
Nidhi | 35 | Text field name in popup should be in same line (Add/Edit Status) Admin> Office Settings > Crew - Joining Types(Permanent Status) |  | NEW
Nidhi | 36 | Header should not have colour. Admin > User Vessel Assignment |  | NEW | Remove this
Nidhi | 37 | Popup is partially visible Crew > Admin> Crew Welfare Library Crew> Crew Interview > Interview Question Bank Operations> Worklist(Add New Task) |  | NEW
Nidhi | 38 | Add New Seniority Reward Year button is overlapping. Crew > Admin > Company Seniority Reward |  | NEW | Remove this
Nidhi | 39 | Content and scroll bar at bottom hides behind when scroll though spaces are available in popup. Crew> Admin> Contract Type |  | NEW
Nidhi | 40 | No columns are present and popup is not properly visible. Crew> Admin > Cash Advance Limit |  | NEW
| 41 | No contents header and popup is not properly visible. Crew > Admin> Oil Majors |  | NEW
| 42 | Outline is not proper and no table line.(Crew Matrix Configuration) Crew > Admin> CrewMatrixConfig |  | NEW
| 43 | Link text "Addition Rule" is partially visible. Crew> Admin> Oil Majors Rule Mapping |  | NEW
| 44 | Popup is not visible. Crew >Admin> Schools |  | NEW
| 45 | Create New Questionnaire popup tab is not proper. Crew> Crew Interview >Create Interview Sheet |  | NEW
| 46 | Content and scroll bar at bottom hides behind when scroll though spaces in popup(click Evaluation Scheduling-Ranks not yet selected). Crew> Crew Evaluation > Evaluation Planning |  | NEW
| 47 | No popup tab when clicked on "New Card" Button. Crew> Crew Accounts >e-Card Kitty |  | NEW
| 48 | Search & Add Pax popup is partially visible. Travel > New Travel Request |  | NEW
| 49 | New FBM text and its icon is overlapping. Quality> FBM |  | NEW | Need screenshot
| 50 | Add Follow-up popup is not visible. Quality > Job Risk Assesment> Risk Assessment>details page |  | NEW
| 51 | Add New Type popup is partially visible. Quality> Job Risk Assesment > JRA Types |  | NEW
| 52 | Add New Rating button is overlapping. Quality> Job Risk Assesment >Risk Ratings |  | NEW | Remove this
| 53 | Add New Category popup is partially visible. Quality > Job Risk Assesment> Work Category |  | NEW
| 54 | Extra Radio button ,Department linktext and textfield appears. Purchase> Admin> Catalogue/Items |  | NEW | Need screenshot
| 55 | Column name should be "Requisition Type" instead of "Department"(Question). Purchase > Admin> Purchase Questionnaire |  | NEW | Remove this
| 56 | "Export to Excel" icon should be visible instead of linktext. Purchase> Purchase Process |  | NEW | Remove this
| 57 | No scroll bar in Supplier dropdown.(Click on Pending Delivery Update) Purchase> Purchase Process |  | NEW | Remove this
| 58 | Extra dropdown text"Department" Purchase> Reports > Machinery Listing |  | NEW | Remove this
| 60 | Search icon is not visible. Technical > Admin> Equipment List |  | NEW | Need screenshot
| 61 | "Sub System Location" allignment is not proper when click on job code. Technical > PMS > Jobs Status |  | NEW | Remove this
| 62 | Popup outline appearance is not proper. Technical> PMS > Jobs History(Add FeedBack) |  | NEW | Need screenshot
| 63 | Search and Vessel Location allignment is not proper. Technical > PMS> Jobs Library |  | NEW | Need screenshot
| 64 | Sets Ins and Sr.no. allignment is not proper when clicked on action icon Technical > PMS > Machinery Change Request |  | NEW | Remove this
| 65 | Job Code , Job Card No., Job Status allignment is not proper. Technical > PMS > UnPlannned Job Details |  | NEW | Need screenshot
| 66 | Grid allignment is not proper Technical> Vessel Inspection > Attendance Calendar |  | NEW
| 67 | Extra" Export to Excel" is partially visible at the bottom. KPI> Crew Retention New |  | NEW
Nidhi | 68 | For IE: Alignment issue for Hiring Details Crew >> Add New Crew |  | NEW | Need screenshot
Nidhi | 69 | Add New Questionnaire Popup is partially visible Crew >> Crew Interview >> Create Interview Sheet Screenshot is shown on sheet 2 |  | NEW | Need screenshot
Nidhi | 70 | Text "Save Evaluation Configurations" should be highlighted in grey color Crew >> Crew Evaluation >> Evaluation Configuration |  | NEW | Remove this
Nidhi | 71 | Show Medical History Details Popup partially visible when clicked on Details Crew >> Reports >> Crew Medical History Viewer Screenshot is shown on sheet 2 |  | NEW
Nidhi | 72 | PI List allignment is not proper it overlaps the graph Crew >> Reports >> Crew Retention Rate Screenshot is shown on sheet 2 |  | NEW
Nidhi | 73 | " Qtn. User List :" Allignment not proper Travel >> Admin >> Travel Qtn UserAssignment Screenshot is shown on sheet 2 |  | NEW
Nidhi | 74 | Add attachment popup and Send RFQ popup is partially visible Travel >> Travel Request Index |  | NEW
Nidhi | 75 | Form Type and Form Status alignment is not proper Quality >> FMS >> FMS Main Screenshot is shown on sheet 2 |  | NEW
| 76 | Suggestion: Atleast Main menu should be highlighted for Detail pages which don’t have menu's.( Eg: "Crew" should be highlighted for Crew Details,Workflow,Interview sheet pages) |  | NEW
Nidhi | 77 | For IE: Instead of counts,it is showing "loading..." for Total Jobs ,Total Overdue Jobs and Total Critical Overdue Jobs Technical >> PMS >> Jobs History Screenshot is shown on sheet 2 |  | NEW
Nidhi | 78 | For IE: Job Code,Job Card No and Job Status alignment is not proper Technical >> PMS >> UnPlannned Job Details Screenshot is shown on sheet 2 |  | NEW
Nidhi | 79 | For IE: Number circle is not present Technical >> Worklist >> Worklist Index Screenshot is shown on sheet 2 |  | NEW
Nidhi | 80 | For IE: Vessel Alignment is not proper under Add New Job Technical >> Worklist >> Worklist Index Screenshot is shown on sheet 2 |  | NEW

## Sheet2
21
22
25
28
MenuDesign
Local Jibe
32
33
34
| Admin > Office Settings> Office Attachment Rule | [9 empty] | Admin >Office Settings> Vessel Attachment Rule
35
|  | Admin > Office Settings > Crew - Joining Types | [8 empty] | Local Jibe
37
41
Crew > Admin> Oil Majors
Local Jibe
44
46
Crew >Crew Evaluation > Evaluation Planning
Local Jibe
67
[6 empty] | KPI > Crew Retention New | [6 empty] | Local Jibe
69
Local Jibe
Actual
70
Local Jibe
Actual
71
|  |  |  | Actual | [6 empty] | Local Jibe
72
Actual
Local Jibe
73
|  |  | Actual | [5 empty] | Local Jibe
75
|  | Actual | [5 empty] | Local Jibe
77
|  |  | Actual | [6 empty] | Local Jibe
78
|  |  | Actual | [6 empty] | Local Jibe
79
|  |  | Actual | [6 empty] | Local Jibe
80
| Actual | [5 empty] | Local Jibe