## Development Features
Development features list
| JIT : | 10517
| No. | Date | Feature Reference | Feature description | DEV. Comment/Query | BA/Client Response | Status (to be filled once developed) | Remarks
| 1 |  | 4.1 Notification screen -> 4.1.1 | Currently when grouping by read/unread, read is shown first. It needs to be reversed, so unread items display first. | Noted
| 2 |  | 4.1 Notification screen -> 4.1.2 | Add the module and tab related to the notification to the messages (for example, if a new notification regarding new vessel drill arrives, the notification will show "Module: Training \ Vessel Training". See mock-up for details) | 1 - Current system not storing module details, So need to store module details when message is send from office. This changes will be done at office side too? | Not sure why it is required on the office side. Anyway, same page in the office can appear in different menus, so the system should prompt only the on board menu path.
| 3 |  | 4.1 Notification screen -> 4.1.3 | By default, the selection will be goruped to the read/unread and will be sorted from the newest to the oldest. | Noted
| 4 |  | 4.1 Notification screen -> 4.1.4 | Currently read messages are not removed from the notification center. Read messages should be removed after 30 days (please advice of the proper time. Note that the deletion is only on the UI level, and the messages will remain in the database) | Noted. Please confirm days limit? This will filter on read date basis only? | Please store it for 30 days. Not sure about the second question. The message will be deleted 30 days after arriving, only if it was already opened/read. I hope that clears your question
| 5 |  | 4.2 Message Dialog -> 4.2.1 | Add new button to "Mark as Unread". Clicking this button will close the message dialog, and will leave the message in unread status (view mockup for full details) | Noted
| 6 |  | 4.3 Email Icon -> 4.3.1 | The email notification icon on the top right will display the amount of new notification received since last time the icon was pressed (regardless of the number of unread emails). | Email icon counter is refreshed only on login on to to system ,after login if user reset email icon counter then it will be set as 0 and this will be refreshed only after login again,Is this ok? email notification icon on the top right will display the amount of new notification- In this we need to show count on icon? Eg - if I have 20 new notifications then I need to show 20 on icon? | Email should be refreshed constantly, not only after log in. if the system is always open, then the master will never note for new messages. My suggestion is that it will be linked to the sync time. So whenever the system is synced, the icon will be refreshed (check for new messages. Icon - correct. Display the number of new notifications on the email icon
| 7 |  | 4.3 Email Icon -> 4.3.2 | Clicking the email icon will reset the number to 0, and will open the message dialog showing the the number of new notifications, and number of total unread message | 1- As per specifications message prompt as A- number of new notifications B- Number of unread messages 2- As per mock-up it will prompt as (number of new notification + Number of unread messages)ie 1+20 eg- "you have 21 new messages". 3- Exactly which format of messages need to prompt A/B A- "you have 21 new messages". B- "21 unread messages" | Option one is the correct one. The system should display two lines: 1. You have XXX new messages 2. You have YYY unread messages
| 8 |  | 4.3 Email Icon -> 4.3.3 | After reseting the notifications, the red icon will not be shown until a new notification arrives | Noted,Need new icon | Why? Please talk with Kiran
| 9 |  | 4.3 Email Icon -> 4.3.4 | Clicking the number of "unread emails" will redirect to the dashboard | 1- on message dialog "unread emails" is clicked then redirect to the dashboard ? 2- As per mock-up on click on "95 unread messages" it will redirect to dashboard. | Not clear. After clicking the email icon, a popup with the number of new notifications and unread messages will appear. Clicking on this popup (either one of the two lines) will redirect to the dashboard
| 10 |  | 4.3 Email Icon -> 4.3.5 | Loging out will not reset the number, so if the crew logs out, and logs in again he will see the number of notifications he had last time he logged out + the new notifications | Noted
| 11 |  | 4.4 New notifications -> 4.4.1 | The onboard module will be able to receive new notifications according to client's request (see "client change request" section 2.1) | Listed multiple modules from office side need to change most of office procedures and need to estimate it seperately | Not clear. Should be discussed.
| 12 |  | 4.5 Access rights -> 4.5.1 | Currently there will be no change for the access/viewing rights. In th enext phase a new admin screen will be added. | Next Phase noted
| 13 |  | 4.5 Access rights -> 4.5.2 | For each new notification, client must determine who will see the notification.
| 14 |  | 4.5 Access rights -> 4.5.2 -> 4.5.2.1 | "Personal" - the crew that initiated the message. For example - crew evaluation
| 15 |  | 4.5 Access rights -> 4.5.2 -> 4.5.2.2 | "Rank" - the ranks that will be able to see the message (can be multiple ranks) | If there are more than one crew menber with one rank present ONBD then how the "reset notification" functionality should work ?. "reset notification" should be maintained for each crew individually or not ?. | Yes. Messages will be received based on rank. Notifications and read/unread will be maintained individually based on the user itself
| 16 |  | 4.5 Access rights -> 4.5.2 -> 4.5.2.3 | "Public" - all crew on the vessel will be able to see the notification | This notification is read by 1 of onboard crew then this should be available as new to other crew ? This notifications will be received by all crew members present in vessel at the moment? After receiving this notification three crew members onboarded in vessel then this new notifications should be display to them? If yes,Then what will be notification life span ? | Think of it as if I'm sending an email to 30 people. Each of them will receive a private message, and it will be read/unread based on his own action (regardless if someone else also read this message). The notifications will be sent only according to the crew onboard at the moment.
| 17 |  | 4.5 Access rights -> 4.5.3 | Currently there is no option to combine the option above (so "personal" cannot be mixed with "ranks").